## projectcontribution
You should clearly describe your contribution to the group project in each category. (This is not the final iteration contribution. It is the whole semester contribution)
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Zak Kysar | Touched on all sections | Yes, some. | Touched all section. |  | Yep | Yes | Self testing the website. | Yes, with server, ftp details, domains purchase, etc. | Yes | Cool project, thanks!
Rattikarn Dudley | Requirement Analysis part | Almost all parts | Class Diagram | Testing Report | Yes | Yes | Automated testing | - Deployment - Implementation main features | - Yes via Slack with crew | Good Expereince with c# Learn asp. net
Connor Richmond | Updated all sections of the document each iteration and addressed professor comments | Yes, some. | Worked on all sections and updated with changes made throughout iterations | Contributed to testing plan | actively created and presented each presentation (minus 1 that I was absent for) | Yes, some. Started early on with some code contributions. Later focused mainly on peer coding | Manual testing of site and opened issues on git with any bugs found | Set up deploy tool to sync text editor with our server. Managed most git merges and repository changes | Actively contributed in team meetings to form plans for each iteration. Was in constant communication with the team over slack! | Loved working with the team and I miss them already!
Juan Sanchez | Main contribution on QA plan, defect management and testing defintion | Created used stories and stories for chrores | Added ER and Relational Schema and database documentation, UI flow logic | Testing report and test cases documentation and test metrics | Yes | Yes | Automated testing design and implementation. DB testing for data integrity | Yes, DB deployment to server and comment feature implementation | Yes via slack | Good experience of full stack implentation

## Zak Kysar
Role: Backup Project Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 2 | 2 | 0.5 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Get all access | Learning | Learn more | ? | ?
2 | 09/14-09/20 | 5 | 4 | 1 |  | 1 | 1 |  |  |  | 2 |  |  | Got organized, thought about requirements | Learning | Will start to implement next week. | Start implementation. | 6?
3 | 09/21-09/27 | 6 | 5 | 1 |  |  | 1 | 1 | 1 |  | 1 | 1 |  | Set up hello world website. Took Juan sql statemnts and made table. | Deciding how to manage the code, where to update it, where to keep golden source, etc. | All issues will be resolved this week. | Dispay data from a table. | 6?
4 | 09/28-10/04 | 6 | 3 | 1 |  |  | 1 |  | 3 |  | 1 | 1 |  | Implemneted add and display projects. | Decided how to connect to SQL database. | Managment on who is doing what. | More coding, not sure yet, need to meet to figure that out. | 6?
5 | 10/5-10/11 | 8 | 7 | 1 |  |  |  |  | 6 | 1 | 1 |  |  |  | Setting team up with IDE. Found a bug in view project page, did not know how to handle null. | Get IDE set up for everyone. | Search | 6
6 | 10/12-10/18 | 6 | 5 | 1 |  | 1 | 2 |  |  | 1 |  | 1 |  | Helped with presentation and testing of new code on server. | Vacation. | Keep moving. | cleaning and advanced search, maybe help with login. | 10
7 | 10/19-10/25 | 6 | 5 | 1 | 1 - requirement analysis - built Jira plan 3 - implementation - Migrated git master to ftp site 4 - test - tested a couple of bugs. 5 - communication/management - worked on docs and comunicated how to accomplish a few tasks 6 - configuration/environment - Worked on design pattern of the site, builiding the thought for it. |  | 1 |  | 1 | 1 | 1 | 1
8 | 10/26-11/01 | 6 | 5 | 1 | Individual Task Breakdown 0 - learning: learned all about design patterns and architecture patters. 2 - design - built design patters and atrchitecture patterns. 5 - communication/management - worked on managing teams and driving code projects 6 - configuration/environment - worked on docs and advised 7 - unclassified: resolved comments on our SDD and SPPP. | 1 |  | 1 |  |  | 1 | 1 | 1
9 | 11/02-11/08 | 4 | 3 | 1 | Individual Task Breakdown 0 - learning: learned testing techniquies and more about design diagrams. 4 - test - tested Ratikarn log in page | 2 |  |  |  | 1
10 | 11/09-11/15 | 6 | 3 | 2 | Individual Task Breakdown 0 - learning - learning about visual studio and how to publish projects. 2 - design - Spent two hours doing research on design and documentation update. 4 - test - spent an hour looking at Rattikarn's new website. It does not have all the functionality that we did have. 5 - communication/management - we met for two hours to discuss how to vesrion control Ratikarn's new code. | 1 |  | 2 |  | 1 | 2
11 | 11/09-11/16 | 11 |  | 4 | Individual Task Breakdown 1 - requirement analysis - In meetings: talked about bugs and pivotal tracker and what each of us are going to do. 2 - design - Had to get Rattikarn's code into a state that all of use could edit, instead of being in a "compressed state." This required refactoring code in files and rearranging file structures, redoing the web.config file, and setting up another URL for our new test environment. Oh, that too, we made a new test environment that is going to help us alot. 3 - implementation - In meetings discussed how we are going to implement the rest of the site and tried to finalize design pattern. 4 - test - confirmed refactoring of site worked for all pages. 5 - communication/management - Worked through how we are going to manage merging Rattikarns code into something we can all edit. |  | 1 | 7 | 1 | 1 | 1
12 | 11/09-11/17 | 6 |  | 0 | Individual Task Breakdown 0 - learning - Learned Rattikarn' code. 3 - implementation - implemented search. This required editing a few pages and trying out new code, testing, etc. 4 - test - Tested the new search code and worked thorugh a bug with the string changing. | 1 |  |  | 4 | 1
12 | 11/09-11/18 | 10 | 8 | 2 | Individual Task Breakdown 2 - design - thought about new software arch 3 - implementation - helped with implementation ideas 4 - test - tested new solution. Looked at use cases, thought about final presentation and flow of events. 5 - communication/management - communicated SPP and SDD edits, help think through what needed to be done for final presentation. |  |  | 1 | 1 | 3 | 3

## Rattikarn Dudley
Role: Security Lead
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 10 | 9.5 | 0.5 | 0 - Learning tools : Github, Docker, Jenkin +5 | 9 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | - Get all the environment set up | - No assign implement role to members | - Assign role to team member | 10 | 20
[5 empty] | 0 - Learning the SPPP from the team leader +2 | [8 empty] | - Start to fill all the requirement documents |  | - front-end and back end roles
[5 empty] | 0 - Learning Pivital tracker +2 | [8 empty] | - Assign role in privital tracker
6 - Setup Atom IDE +0.5
5 - Minute meeting with a group +0.5
| 09/14-09/20 | 13 | 12 | 1 | 6 - Setup Docker +5 | 3 | 0 | 2 | 0 | 1 | 1 | 6 | 0 | - Assign Epic story in pivital tracker | - Docker is not work in Windows 10 Home | - Install virtual machine with Linux OS | 10 | 20
[5 empty] | 6 - Setup Jenkin +1 | [8 empty] | - Github commit to a team repository |  | - Install Docker and Jenkins via Linux OS
[5 empty] | 0- Learning Jenkin +2 | [8 empty] | - Assign info description in Team.md
0- Learning Django +1
2 - Design Pivital tracker Epic +2
5- Team meeting +1
2 |  |  |  |  | 4- Testing docker and Jenkin server +1
3 | 09/21-09/27 | 18 | 17 | 1 | 6 - Setup Django +2 | 7 | 0 | 2 | 6 | 0 | 1 | 2 | 0 | - Implement pivital tracker for interation 1 | - Language use in backend not finalize | Finalize the backend language use | 10 | 20
[5 empty] | 0 - Learning Django +2 | [8 empty] | - Pull skeleton from master branch | - Implementation role still not assign | Assign a specific implementation role
[5 empty] | 0 - Learning Spring Security + 2 | [8 empty] | - Create a rkFeature for adding feature logi | - meeting agenda not assign before meeting | Create a meeting agenda
[5 empty] | 3 - Implement Pivital Tracker for iteration 6 | [8 empty] | - Finish some of UI mock up pages | - meeting minutes not specific | Polishing minutes meeting
2- Design UI mock up +2
5 - Teaming meeting and slack +1
0 - Leaning Django with SQL server +3
4 | 09/28-10/04 | 7.5 | 6.5 | 1 | 0 - Learning ASP.NET +2 | 3 | 0 | 0 | 2 | 0 | 1 | 1.5 | 0 | - MS VS and MS SQL set up | - Obvious roles still not assign | - Obvious assign role to each member | 10 | 20
[5 empty] | 0 - Learning C# +1 | [8 empty] | - Finalized language and tools | - Docker and SQL is complicated to set up in Ubuntu
6 - Set up VS +0.5
6- Setup MSSQL in Docker +5
3- Implement Login web page skeleton +2
5 - Team meeting +1
5 | 10/5-10/11 | 16 | 15 | 1 | 2- Implement UI site for sign up +2 | 0 | 0 | 4 | 0 | 5 | 1 | 0 | 0 | - Deployed UI styling to main server | - Having less time to focus on a project due to quiz to | - Stay up late to have more time to study | 10 | 20
[5 empty] | 2- Implement UI site for user profile +2 | [8 empty] | - Testing html and current c# cs html file | differencence class
[5 empty] | 4- Testing add project page via cshtml file +5 | [9 empty] | - Github issue lost all files due to mis implement | - Reset commit state to pull lost file
5- Team Meeting +1
2- design site diagram +6
6 | 10/5-10/11 | 17 | 16 | 1 | 0- Learn MVC ASP.Net +3 1- Risk Management +10 5- Team Meeting +1 2- Design UML class diagram +2 | 3 | 2 | 0 | 0 | 2 | 1 | 0 | 0 | - Fill out the risk management requirement document by researching from the internet to understand how to write and see some sample how to define the risk management. | - There are no class diagram implemented in a project. - The Class UML is based on a possible way not an acutal code. | - Implement a class in a project for a good practice and be able to analysis project in agile in a future. | 10 | 20
7 | 10/12-10/25 | 11 | 10 | 1 | 0- Learn sonarqube +4 4- Test Design +2 5-Team meeting +1 2- Resposive Desing +4 | 4 | 0 | 4 | 0 | 2 | 1 | 0 | 0 | - Manual test frontend and all functionalities in html | - Class not define and google login are not started | - Define classes and their relationship - Start to implement log in function | 10 | 20
8 | 10/26-11/01 | 15 | 14 | 1 | 3- Resposive implementation +11 4- Testing results +3 5- Team meeting +1 | 0 | 0 | 0 | 11 | 3 | 1 | 0 | 0 | n/a | n/a | - Cannot start a progress for analysis design class digram, unit testing and not meet requirement in pivital tracker. | 10 | 20
9 | 11/02- 11/09 | 26 | 25 | 1 | 2- Implementation +25 5- Team meeting +1 | 0 | 0 | 25 | 0 | 0 | 1 | 0 | 0 | - Refactoring code by create different classes - Deploy the code via VS deployment method | - Not in a same page with the team members - Cannot test directly via a server - The deployement have to done via VS - The environment need to use only VS since there is an issue with IIS security block to deploy directly from the server. | - Set up a VS for all members | 10 | 20
10 | 11/10-11/17 | 16 | 15 | 1 | 0- Learn how to write unit testing in c# +2 5- Team meeting +1 6- Install Selenium and Testing unit framework +1 4- Testing +12 | 2 | 0 | 0 | 0 | 12 | 1 | 1 | 0 | - Desing testing pattern | - Not understand how design patter work very well | - Learn how design pattern work with unit testing | 10 | 20
11 | 11/18-11/24 | 20 | 19 | 1 | 2- Implement class password, debugging unfuntioning methods + 19 5 - Team meeting +1 | 0 | 0 | 19 | 0 | 0 | 1 | 0 | 0 |  |  |  | 10 | 20
12 | 11/24-12/06 | 20 | 19 | 1 | 2 - Refectoring a connecting class (DBs) +5 5- Team meeting +1 4- Implement Testing unit +3 0 - Learn about facde design in unit testing +2 2- Implement facde in testing selenium +9 | 2 | 0 | 14 | 0 | 3 | 1 | 0 | 0 | - Refactoring redundancy codes | - Not understand platform well how to identify class inheritance since the platform already inherited by the system. | - Learn how to inherit class in this platform. | 10 | 20

## (JP) Juan Sanchez
Role: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 3 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | get access | learning curve | NA | NA | 2
2 | 09/14-09/20 | 5.5 | 5 | 0.5 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | Writte SPPP QA reqs | IDE selection and git hub set up for defect tracking | Meet with team to decide | SQL for testing | 2
3 | 09/21-09/27 | 5.5 | 5 | 0.5 | 2 | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | Database architecture. Understand entities requirement and constraints. Create ER Diagram | Determine user types. Already have STUDENT, FACULTY. Maybe need OTHER type of user | NA | Complete ER diagrams and Relational Database schema after feedback from team with constraints | 3
4 | 09/28-10/04 | 5 | 4 | 1 | 2 | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | Create relational DB schema | none | first draft created need team approval | SQL for table creating and populate tables | 3
5 | 10/5-10/011 | 8 | 6 | 1 | 3 | 2 | 2 | 1 | 3 | 0 | 0 | 0 | 0 | SQL create tables, constraints and tuple samples | On delete action need to test data integrity and tables update cascade | Need further testing | Complete all tuples and finish DB implementation | 3
6 | 10/12-10/18 | 3 | 2 | 1 | 3 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | Presentation and documentation | none | none | implement flow chart for UI | 4
7 | 10/19-10/25 | 4 | 3 | 1 | 0 - Learning - learn flow diagram Lucid chart 2 - implementation - Create UI flow diagram 5 - communication/management - worked on docs and comunicated chart | 1 | 2 | 0 | 0 | 0 | 1 | 0 | 0 | UI flow diagram chart logic and listeners | logic corrections and naming corrections | closed | implement flow on user interface for user story | 5
8 | 10/26-11/01 | 7 | 6 | 1 | Individual Task Breakdown 0 - Learn CSS/HTML files 1 - Review UI 2 - Design buttons and pages 3 - Implement IU flow 5 - SPPP/SDD updates | 2 | 0.5 | 2 | 1 | 0 | 1 | 0 | 0 | Created pages for Comments and User Profile | Need to test buttons and redirect | open |  | 6
9 | 11/02-11/08 | 6 | 6 | 1 | Individual Task Breakdown 0 - learning visual studio and Design pattersn 2 - design project structure VS and classes 3 - implementation Design pattern to project 5 - communication presentation and documentation
10 | 11/09-11/15 | 6 | 6 | 1 | Individual Task Breakdown 0 - More Design patterns 2 - design patterns revisit 3 - implementation Design pattern to project 5 - communication presentation and documentation
11 | 11/16 - 12/5 | 18 | 17 | 1 | Individual Task Breakdown 0 - More Design patterns 2 - design patterns revisit 3 - Automated testing Visual Studio 4 - Run test cases and document bugs 5 - communication presentation and documentation

## Connor Richmond
Role: Project Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 3 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | setup environment | setup confusion |  |  | 3
2 | 09/14-09/20 | 3 | 2.5 | 0.5 | 2019-06-01 | 0 | 1 | 1 | 0 | 0 | 0 | 0.5 | 0 | Requirement definitions | n/a |  |  | 2
3 | 09/21-09/27 | 3 | 2.5 | 0.5 | 2 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | SDD and SPP updates | n/a |  |  | 3
4 | 09/28-10/04 | 4 | 3 | 1 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | Manage git and handle release |  |  |  | 2
5 | 10/5-10/11 | 4 | 3.5 | 0.5 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | Start User Authentication Process | testing environment | Next steps to be troubleshooted shortly |  | 2
6 | 10/12-10/18 | 7 | 6 | 1 | 2019-02-05 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | Focus on SPPP + SDD revisions, Risk management documentation, and presention drafting |  |  |  | 7
7 | 10/19-10/25 | 6 | 5 | 1 | 2 - design - updating SDD to reflect new architecture 5 - communication/management - update SPPP and Risks doc 6 - configuration/environment - Merge git branches and define code deploy process | 0 | 0 | 2 | 0 | 0 | 2 | 1 | 0 | Update documentation and keep git branches updated/clean. Handle merge conflicts and update presentation | merge issue introduced bug | fix merge issue |  | 6
8 | 10/26-11/01 | 5 | 4 | 1 | 2 - design - updating SDD further. 5 - communication/management - update SPPP and Risks doc 6 - configuration/environment - clean master branch and merge new features | 0 | 0 | 2 | 1 | 0 | 1 | 1 | 0 | Update git and team docs |  |  |  | 5
9 | 11/02-11/08 | 6 | 5 | 1 | 0- learn visual studio development practices 2 - design - updating SDD 5 - communication/management - update SPPP 6 - configuration/environment - git management and visual studio setup | 1 | 0 | 0.5 | 0 | 0 | 1.5 | 2 | 0 | Updating team docs and learning about visual studio for team development process
10 | 11/09-11/15 | 5 | 3.5 | 1.5 | 2 - design - updating SDD further. 5 - communication/management - update SPPP and Risks doc 6 - configuration/environment - clean master branch and merge new features. Further debug visual studio issues for team development | 0 | 0 | 1 | 0 | 0 | 1 | 1.5 | 0 | most time spent this iteration configuring visual studio for future team development. Overall process hinges on getting VS stetup.
11 | 11/16-11/22 | 6 | 5 | 1 | 2 - design 5 - communication/management - update SPPP and Risks doc 4 - testing of site 6 - configuration/environment - Open git issues resulting from manualtesting | 0 | 0 | 1 | 0 | 2 | 1 | 1
12 | 11/23-11/29 | 6 | 4.5 | 1.5 | 2 - design 5 - communication/management - update SPPP and Risks doc 4 - testing of site 6 - configuration/environment - Open git issues resulting from manualtesting
13 | 11/30-12/08 | 10 | 5 | 2 | 5 - communication/management - update SPPP and Risks doc. Create final presentation 4 - testing of site 6 - configuration/environment - working with team to get working version of site live | 0 | 0 | 0 | 1 | 3 | 3 | 1

## Molla Negash
Role: Design
Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 6 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | discussing on project title and access | learing | getting more ideas | project proposal | 2
2 | 09/14-09/20 | 4 | 4 | 0.5 | 2 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | project proposal design | none | none | none
3 | 09/21-09/27 | 5 | 4 | 1 | 0.5 | 1 | 1.5 | 0 | 0 | 0.5 | 0 | 0 | discussing on ER diagram | Determine user types. | none | Complete UML | 2
4 | 09/28-10/04 | 6 | 4 | 0.25 | 0.25 | 0 | 0.5 | 0 | 0 | 0.15 | 0 | 0 | creating tuples | violation of foreign keys | descussing with team members | none | 1
5 | 10/5-10/011 | 5 | 4 | 0.25 | 1 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | collecting sample projects for test plan | none | share to members | learning how to connect browser to the server | 0.5
6 | 10/12-10/018 | 0.5 | 0.5 | 0 | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | updating progress report | time conflect | none | learning how to connect browser to the server | 0.5

## Summary-GroupIterationProgress
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan
0 | 09/06-09/20
1
2
3
4
5

## Metrics-GroupIterationProgress
iteration | Date range | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks
0 | 09/06-09/20
1
2
3
4
5