## Sheet1
Team 4 Metrics Tracker |  |  | ITERATION
METRIC | Unit | Type | 0 | 1 | 2 | 3 | 4 | 5 | Coment
Product Complexity | KLOC | Product | 500 | 1200 | 2065 | 2066 | 2078 | 2089
File Count | # Files | Product | 4 | 10 | 17 | 27 | 27 | 51
Defect Density | # Defects / KLOC | Product | 0 | 0 | 0.00048426 | 0.00096805 | 0.00096246 | 0.0043083
Defect Count | # Defects | Product | 0 | 0 | 1 | 2 | 2 | 9 | https://github.com/bumetcs673f19/cs673-project-team-4/issues
Customer Issues Count | # Issues | Product | bar: ITERATION 0 to ITERATION 5
Cost | # Hrs per Iteration | Product | 43.5 | 53 | 60 | 64.5 | 64 | 112
Customer Satisfaction | (1 - 5) | Product | bar: ITERATION 0 to ITERATION 5
Test Cases Count | # Test cases total | Process | NA | NA | 1 | 5 | 3 | 18
Test Case Pass Rate | # Passed / # Total | Process | NA | NA | 1 | 5 | 3 | 18
Schedule Adherance | Goal (Days) - Completion (Days) | Process | 0 | 0 | 0 | -2 | 0 | 0
Iteration Improvement | - | - | Use same IDE | Improve Github workflow | Implement more unit testing | Files organization to improve workflow | Issues with IDE and deployment files. Need fiine tuning version control | Software design and architecture should have been more up front
Revisions
Date | Note | Owner
2019-10-04 | Created tracker in G drive | Juan S.
2019-10-15 | Updated Iteration 0-2 | Juan S.
2019-10-31 | Updated iteration 3 | Juan S.
2019-11-13 | Updated iteration 4 | Juan S.
2019-12-04 | Updated iteration 5 | Juan S.