## Sheet1
Team 4 Metrics Tracker |  |  | ITERATION
METRIC | Unit | Type | 0 | 1 | 2 | 3 | 4 | 5 | Coment
Product Complexity | KLOC | Product | ITERATION 0: 500; ITERATION 1: 1200; ITERATION 2: 2065
File Count | # Files | Product | ITERATION 0: 4; ITERATION 1: 10; ITERATION 2: 17
Defect Density | # Defects / KLOC | Product | ITERATION 0: 0; ITERATION 1: 0; ITERATION 2: 0.00048426
Defect Count | # Defects | Product | ITERATION 0: 0; ITERATION 1: 0; ITERATION 2: 1 | https://github.com/bumetcs673f19/cs673-project-team-4/issues
Customer Issues Count | # Issues | Product | bar: ITERATION 0 to ITERATION 2
Cost | # Hrs per Iteration | Product | ITERATION 0: 43.5; ITERATION 1: 53; ITERATION 2: 60
Customer Satisfaction | (1 - 5) | Product | ITERATION 0: 5; ITERATION 1: NA; ITERATION 2: NA
Test Cases Count | # Test cases total | Process | bar: ITERATION 0 to ITERATION 2
Test Case Pass Rate | # Passed / # Total | Process | bar: ITERATION 0 to ITERATION 2
Schedule Adherance | Goal (Days) - Completion (Days) | Process | ITERATION 0: 0; ITERATION 1: 0; ITERATION 2: 0
Iteration Improvement | - | - | ITERATION 0: Use same IDE; ITERATION 1: Improve Github workflow; ITERATION 2: Implement more unit testing
Revisions
Date | Note | Owner
2019-10-04 | Created tracker in G drive | Juan S.
2019-10-15 | Updated Iteration 0-2 | Juan S.