## Zak Kysar
Role: Backup Project Leader
Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified |  |  |  |  | You need to describe each task in detail each week
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 2 | 2 | 0.5 | 0- Learning something +1h | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Get all access | Learning | Learn more | ? | ?
2 | 09/14-09/20 | 5 | 4 | 1 |  | 1 | 1 |  |  |  | 2 |  |  | Got organized, thought about requirements | Learning | Will start to implement next week. | Start implementation. | 6?
3 | 09/21-09/27 | 6 | 5 | 1 |  |  | 1 | 1 | 1 |  | 1 | 1 |  | Set up hello world website. Took Juan sql statemnts and made table. | Deciding how to manage the code, where to update it, where to keep golden source, etc. | All issues will be resolved this week. | Dispay data from a table. | 6?
4 | 09/28-10/04 | 6 | 3 | 1 |  |  | 1 |  | 3 |  | 1 | 1 |  | Implemneted add and display projects. | Decided how to connect to SQL database. | Managment on who is doing what. | More coding, not sure yet, need to meet to figure that out. | 6?
5 | 10/5-10/011 | 8 | 7 | 1 |  |  |  |  | 6 | 1 | 1 |  |  |  | Setting team up with IDE. Found a bug in view project page, did not know how to handle null. | Get IDE set up for everyone. | Search | 6
6 | 10/12-10/018 | 6 | 5 | 1 |  | 1 | 2 |  |  | 1 |  | 1 |  | Helped with presentation and testing of new code on server. | Vacation. | Keep moving. | cleaning and advanced search, maybe help with login. | 10

## Rattikarn Dudley
Role: Security Lead
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 10 | 9.5 | 0.5 | 0 - Learning tools : Github, Docker, Jenkin +5 | 9 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | - Get all the environment set up | - No assign implement role to members | - Assign role to team member | 10 | 20
[5 empty] | 0 - Learning the SPPP from the team leader +2 | [8 empty] | - Start to fill all the requirement documents |  | - front-end and back end roles
[5 empty] | 0 - Learning Pivital tracker +2 | [8 empty] | - Assign role in privital tracker
6 - Setup Atom IDE +0.5
5 - Minute meeting with a group +0.5
| 09/14-09/20 | 13 | 12 | 1 | 6 - Setup Docker +5 | 3 | 0 | 2 | 0 | 1 | 1 | 6 | 0 | - Assign Epic story in pivital tracker | - Docker is not work in Windows 10 Home | - Install virtual machine with Linux OS | 10 | 20
[5 empty] | 6 - Setup Jenkin +1 | [8 empty] | - Github commit to a team repository |  | - Install Docker and Jenkins via Linux OS
[5 empty] | 0- Learning Jenkin +2 | [8 empty] | - Assign info description in Team.md
0- Learning Django +1
2 - Design Pivital tracker Epic +2
5- Team meeting +1
2 |  |  |  |  | 4- Testing docker and Jenkin server +1
3 | 09/21-09/27 | 18 | 17 | 1 | 6 - Setup Django +2 | 7 | 0 | 2 | 6 | 0 | 1 | 2 | 0 | - Implement pivital tracker for interation 1 | - Language use in backend not finalize | Finalize the backend language use | 10 | 20
[5 empty] | 0 - Learning Django +2 | [8 empty] | - Pull skeleton from master branch | - Implementation role still not assign | Assign a specific implementation role
[5 empty] | 0 - Learning Spring Security + 2 | [8 empty] | - Create a rkFeature for adding feature logi | - meeting agenda not assign before meeting | Create a meeting agenda
[5 empty] | 3 - Implement Pivital Tracker for iteration 6 | [8 empty] | - Finish some of UI mock up pages | - meeting minutes not specific | Polishing minutes meeting
2- Design UI mock up +2
5 - Teaming meeting and slack +1
0 - Leaning Django with SQL server +3
4 | 09/28-10/04 | 7.5 | 6.5 | 1 | 0 - Learning ASP.NET +2 | 3 | 0 | 0 | 2 | 0 | 1 | 1.5 | 0 | - MS VS and MS SQL set up | - Obvious roles still not assign | - Obvious assign role to each member | 10 | 20
[5 empty] | 0 - Learning C# +1 | [8 empty] | - Finalized language and tools | - Docker and SQL is complicated to set up in Ubuntu
6 - Set up VS +0.5
6- Setup MSSQL in Docker +5
3- Implement Login web page skeleton +2
5 - Team meeting +1
5 | 10/5-10/11 | 16 | 15 | 1 | 2- Implement UI site for sign up +2 | 0 | 0 | 4 | 0 | 5 | 1 | 0 | 0 | - Deployed UI styling to main server | - Having less time to focus on a project due to quiz to | - Stay up late to have more time to study | 10 | 20
[5 empty] | 2- Implement UI site for user profile +2 | [8 empty] | - Testing html and current c# cs html file | differencence class
[5 empty] | 4- Testing add project page via cshtml file +5 | [9 empty] | - Github issue lost all files due to mis implement | - Reset commit state to pull lost file
5- Team Meeting +1
2- design site diagram +6
6 | 10/5-10/011 |  |  |  | 0- Learn MVC ASP.Net 1- Risk Management 5- Team Meeting 2- Design UML class diagram
7 | 10/12-10/018

## (JP) Juan Sanchez
Role: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 3 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | get access | learning curve | NA | NA | 2
2 | 09/14-09/20 | 5.5 | 5 | 0.5 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | Writte SPPP QA reqs | IDE selection and git hub set up for defect tracking | Meet with team to decide | SQL for testing | 2
3 | 09/21-09/27 | 5.5 | 5 | 0.5 | 2 | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | Database architecture. Understand entities requirement and constraints. Create ER Diagram | Determine user types. Already have STUDENT, FACULTY. Maybe need OTHER type of user | NA | Complete ER diagrams and Relational Database schema after feedback from team with constraints | 3
4 | 09/28-10/04 | 5 | 4 | 1 | 2 | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | Create relational DB schema | none | first draft created need team approval | SQL for table creating and populate tables | 3
5 | 10/5-10/011 | 8 | 6 | 1 | 3 | 2 | 2 | 1 | 3 | 0 | 0 | 0 | 0 | SQL create tables, constraints and tuple samples | On delete action need to test data integrity and tables update cascade | Need further testing | Complete all tuples and finish DB implementation | 3
6 | 10/12-10/018 | 3 | 2 | 1 | 3 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0
7

## Connor Richmond
Role: Project Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 3 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | setup environment | setup confusion |  |  | 3
2 | 09/14-09/20 | 3 | 2.5 | 0.5 | 2019-06-01 | 0 | 1 | 1 | 0 | 0 | 0 | 0.5 | 0 | Requirement definitions | n/a |  |  | 2
3 | 09/21-09/27 | 3 | 2.5 | 0.5 | 2 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | SDD and SPP updates | n/a |  |  | 3
4 | 09/28-10/04 | 4 | 3 | 1 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | Manage git and handle release |  |  |  | 2
5 | 10/5-10/11 | 4 | 3.5 | 0.5 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | Start User Authentication Process | testing environment | Next steps to be troubleshooted shortly |  | 2
6 | 10/12-10/18 | 7 | 6 | 1 | 2019-02-05 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | Focus on SPPP + SDD revisions, Risk management documentation, and presention drafting |  |  |  | 7

## Molla Negash
Role: Design
Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 6 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | discussing on project title and access | learing | getting more ideas | project proposal | 2
2 | 09/14-09/20 | 4 | 4 | 0.5 | 2 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | project proposal design | none | none | none
3 | 09/21-09/27 | 5 | 4 | 1 | 0.5 | 1 | 1.5 | 0 | 0 | 0.5 | 0 | 0 | discussing on ER diagram | Determine user types. | none | Complete UML | 2
4 | 09/28-10/04 | 6 | 4 | 0.25 | 0.25 | 0 | 0.5 | 0 | 0 | 0.15 | 0 | 0 | creating tuples | violation of foreign keys | descussing with team members | none | 1
5 | 10/5-10/011 | 5 | 4 | 0.25 | 1 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | collecting sample projects for test plan | none | share to members | learning how to connect browser to the server | 0.5
6 | 10/12-10/018 | 0.5 | 0.5 | 0 | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | updating progress report | time conflect | none | learning how to connect browser to the server | 0.5

## Summary-GroupIterationProgress
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan
0 | 09/06-09/20
1
2
3
4
5

## Metrics-GroupIterationProgress
iteration | Date range | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks
0 | 09/06-09/20
1
2
3
4
5