## Sheet1
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (1-5 or H/M/L) | Estimated Impact (1-5 or H/M/L) | Estimated retirement Cost (in person hours) | Priority | Responsible engineer | Target completion date | Detailed plan | Status
personel | Loss team members | The lost of team member will impact the schedule, momentum and the direction of the project. | 1 | 5 | 15 | 5 | Connor | 2019-12-16 | Assure files are uploaded and integrated consistently, use knowledge management strategies such as pair programming to understand each other’s work. | active
| add new team members | Adding a new member to the existing team could potentially impact the dynamic of the team. | 1 | 5 | 10 | 5 | Connor | 2019-09-15 | shift one-on-ones to helping the new employee really dig in and start to understand the context of the work she/he will be doing. | non-active
| Lack of motiviation or responsbility | The team must be motivated to make the best decisions in the best interest of the project | 5 | 5 | 20 | 25 | Connor | 2019-12-16 | -Set realistic -Be direct -Praise small victories -Supply feeb back from the start Find ways to foster strong relationships among all members | active
Communication | duplicate work | The issue of duplicate work could impact the team member time and lack of productivity. | 3 | 5 | 20 | 15 | Juan | 2019-10-24 | - the team decides which stories are to deliver and which tasks are to be completed. -If two people know they will be working in similar area, they should participate in the same discussion. | active
| worked on wrong components | Working on wrong components could reduced the productivity delay, cost effective and time management | 3 | 5 | 15 | 15 | Juan | 2019-10-24 | -Use abstract components and abstract concepts as an architrcture buiding block such as UML with a computer diagram | active
| useless work | Writing codes that will not needed at later time caused wasting team members time and decresed the quality time to implementation other components | 5 | 5 | 20 | 25 | Juan | 2019-10-24 | -The members need to understand how the modules service will work with each component, what structure it will have, how it will be tested, debugged and updated | active
Requirements | unclear requirements | Unclear requirement could caused the project delay, cost get double and quaity assurance will be not as expected | 5 | 5 | 25 | 25 | Rattikarn | 2019-10-24 | -Put assumption around team estimate and make it visible to stackholder by document project plan. -Keep refine the requirement more often by meeting up with the team members. | active
| scope creep | Scope creep is typically caused by key project stakeholders changing requirements, or sometimes from internal miscommunication and disagreements. | 5 | 5 | 25 | 25 | Rattikarn | 2019-10-24 | -Monitoring the project's status and baseline scope -Comparing actual work performance measurements with the baseline scope using variance analysis: "How different is the current project from the original plan?" -Determining the cause and the degree of the changes found -Deciding on change requests, i.e. whether corrective or preventive action is needed -Managing all change requests and recommended actions (whether corrective or preventive actions) via the Perform Integrated Change Control proces | active
| requirement changes | The requirement change is a part of software development to increase understading requirements, fix error and changes in interal circumstances. | 5 | 5 | 25 | 25 | Rattikarn | 2019-10-24 | -Traceability required in the changing requirements and should applied in souce, test case , architecture and requirements | active
Management | user stories not update | Not update the ice box to current box in pivital tracker could misleading stakeholders know the project direction. | 5 | 5 | 20 | 25 | Rattikarn | 2019-10-24 | -Requirement lead keep track on minute meeting what is the next user stories to be updated. -Frequently update user stories once a day | active
| Not understand how pivotal tracker works | Team member having a difficulty to understand pivital tracker could create a useless work, wasting time and delay process. | 5 | 5 | 20 | 25 | Rattikarn | 2019-10-24 | -Giving sources and tutorial team members to understand how to monitor, track and apply user stories into their work. | active
Technolgy competence | Not familiar with framework | Framework can help establish better programming practices and appropriate use of design patterns. | 2 | 4 | 10 | 8 | Zak | 2019-12-16 | -Tutoring and practice using a framework -Pair programming for tutorial | active
| Not familiar with the programming language used | It is critical component since our project is based on the programming language. | 5 | 5 | 25 | 25 | Zak | 2019-11-16 | -Tutorial and and practice to be comfortable with language. -Pair working with a person who already profientcy in a languge | active
| Not familiar with unit testing | Unit testing is the process of writing code to test the behavior and functionality of the system. | 1 | 5 | 10 | 5 | Zak | 2019-10-24 | -Tutorial and pair with team members who have expereince with the unit testing. -If no team member familair with the unit test, take time and study together before create a unit test. -Practice and apply to the project | active
| Not familiar with Git | Not familiar with git can easily make a mistake and wasting time, decrese productivity on a project. | 1 | 3 | 5 | 3 | Connor | 2019-11-30 | -Tutorial and pair with team members who have expereince with the git. -Learn 5 basic git commands and practice on a project. -If members do not know linux command, learn to use git via GUI interface. | active
Implementation | detailed problems | Not understand how to implement logic or do not understand how the logic work | 5 | 5 | 20 | 25 | Zak | 2019-11-30 | -Pair programming who working in a same section or function -Document and comment the uncleared section | active
Testing | Not enough testing | This ensure proper performance of the integrated system working as a whole. | 4 | 5 | 10 | 20 | Juan | 2019-11-30 | -Set a minimum unit testing for each case -Audit and check the unit test -Set a minimum the whole process testing -Audit and check a testing each case align with a whole project | active
Integration and deployment | Deployment rush | It is better to deploy when once the sytem run successfully rather than deploy in rush and fail many times. | 5 | 5 | 25 | 25 | Connor | 2019-12-08 | -Release management | active
| Deployment straight though FTP server | Deploy straight toward the web server could create unpleasant features and system failure. | 5 | 5 | 50 | 25 | Connor | 2019-10-16 | -Always eep master branch as a original -Merge master branch to user branch first before starting deploy a process to the server -If it failed, push master file to the server | active
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.